## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the milestone description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use the progress column to add how much of the project you finished by adding a percentage number • Add the day you started your project in the start date column • Finish your calculations by filling in the number of days you need to complete your project in the days column

## Green
Project: Green
Write 1 for milestone flag
Project start date: | 2023-11-01 | [7 empty] | Scrolling increment: | [5 empty] | 0
Milestone marker: | 1
|  | November | [29 empty] | December | [30 empty] | January
 | time axis 2023-11-01 to 2024-01-12
Milestone description | Start | time axis 2023-11-01 to 2024-01-12
Project Deadlines
Draft of report | 2023-12-11 | bar: 2023-11-06 to 2023-12-11
Review of drafts | 2023-12-15 | bar: 2023-12-12 to 2023-12-15
Presentation & final submission | 2024-01-12 | bar: 2023-12-16 to 2024-01-12
Tutorials
ROS tutorials | 2023-11-01 | bar: 2023-11-01 to 2023-11-05
TIAGo tutorials | 2023-11-01 | bar: 2023-11-01 to 2023-11-12
Perception
Researching object detection (YOLOv8) | bar: 2023-11-06 to 2023-11-12
Researching LIDAR integration with camera feed | bar: 2023-11-06 to 2023-11-12
Implementation object detection | 2023-11-06 | bar: 2023-11-13 to 2023-11-26
Integrating point map and camera feed | 2023-11-06 | bar: 2023-11-13 to 2023-11-26
Implementing ultrasonic detection | bar: 2023-11-13 to 2023-11-19
Localization and Mapping
Implement gmapping
Implement amcl
Decision Making
Feasibility study
To add more data, Insert new rows ABOVE this one

## Green_weeks
Project: Green
Write 1 for milestone flag
Project start date: | 2023-11-01 | [7 empty] | Scrolling increment: |  |  |  | 0
Milestone marker: | 1
|  | November |  |  |  |  | December |  |  |  | January
|  | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week
Milestone description | Deadline | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2
Project Deadlines |  | 51: Buffer & report writing
Draft of report | 2023-12-11 | bar: 50
Review of drafts | 2023-12-15 | bar: 50
Presentation & final submission | 2024-01-12 | bar: 2
Tutorials
ROS tutorials | bar: 44
TIAGo tutorials | bar: 44 to 45
Perception
Researching object detection (YOLOv8) | bar: 45
Researching LIDAR integration with camera feed | bar: 45
Implementation object detection | bar: 46 to 47
Integrating point map and camera feed | bar: 46 to 47
Implementing ultrasonic detection | bar: 46
Localization and Mapping
Implement gmapping | bar: 45 to 47
Implement amcl | bar: 45 to 47
Decision Making
Implement decision making algorithm | bar: 47 to 48
Integration
Integrating perception with localization & mapping | bar: 48
Integrating decision making with the rest | bar: 49
To add more data, Insert new rows ABOVE this one